## GweedoreDP Backlog
Type | Epic/US Name | Epic/US Description | Epic/US AC | Linked To | Priority | Issue Points | Sprint | Assigned To | Issue Status | Updated by | Update Date
User Story1 | Portal Monitoring | As a User I want to enable portal monitoring using Amazon CloudWatch console so that I am notified when system resources are over utilized to take proactive action | Given: GweedoreDP is running on AWS Portal monitoring is enabled When: System resources are overutilized Then: I will be notified if system resource usage is per below CPU Utilization: greater than 50% Network Utilization Resource Count Alarm for CPU Usage Alarm Alarm for Billing Alarm | Epic Name: Infrastructure Setup | Low |  | Sprint3 | Gary | Open
Task1 | CPU utilization | The goal of this task is to enable monitoring for CPU utilization |  | User Story1 - Portal Monitoring | Low |  | Sprint3 | Gary | Open
Task2 | Network Utilization | The goal of this task is to enable monitoring for Network utilization |  | User Story1 - Portal Monitoring | Low |  | Sprint3 | Gary | Open
Task3 | Resource Count | The goal of this task is to monitor resource count |  | User Story1 - Portal Monitoring | Low |  | Sprint3 | Gary | Open
Task4 | Alarm for CPU Usage Alarm | The goal of this task is to set alarm for CPU Usage Alarm |  | User Story1 - Portal Monitoring | Low |  | Sprint3 | Gary | Open
Task5 | Alarm for Billing Alarm | The goal of this task is to set alarm for Billing Alarm |  | User Story1 - Portal Monitoring | Low |  | Sprint3 | Gary | Open
User Story2 | AWS Indentity & Access Management | As a User I want to set Up AWS Indentity & Access Management so that I can create user roles and privileges for GweedoreDP users | Given: I have successfully logged in with valid AWS Account When: Navigate to setup AWS Indentity & Access Management Then: Below user roles and privileges are created successfully One root user which will own the AWS Acount Seven IAM Users , one for each team Marvel Member A user admin group and asign 4 or the 7 team members to the group | Epic Name: Infrastructure Setup | High | 6 | Sprint1 | Jeremy | Open
Task1 | Create one root user | Create one root user which will own the AWS Acount. |  | User 2 - AWS Indentity & Access Management | High |  | Sprint1 | Jeremy | Open
Task2 | Create seven IAM Users | Create seven IAM Users , one for each team Marvel Member |  | User 2 - AWS Indentity & Access Management | High |  | Sprint1 | Jeremy | Open
Task3 | create a a user admin group | create a a user admin group and asign 4 or the 7 team members to the group |  | User 2 - AWS Indentity & Access Management | High |  | Sprint1 | Jeremy | Open